# Appendix C

## Prospecting Sprint Plan (4-6 weeks)

| Week | Minimum activities | Outputs |
| --- | --- | --- |
| 1 | Finalize target list; complete employer profiles; prepare assets; assign owners | Target list + profiles; outreach calendar |
| 2 | Initial outreach to Tier 1–2; schedule discovery calls | Discovery calls scheduled |
| 3 | Discovery calls; document commitments; refine list | Commitments log complete |
| 4 | Design meetings; select pilot model; finalize agreements | Partnership plan + agreements |
| 5–6 | Launch pilot and begin tracking; early feedback loop | Starts/participation; early retention plan |